## Slide 1
11th of September 2015
4BOX STATUS REPORT
NMS – New Messaging Service

## Slide 2
NMS
PM/Lead
Week/Yr
RAG rating
LGU
35/15
Green
  Work Orders Signed
  Co-Existence environment upgraded
  Detailed Design completed
  Migration tools testing
  Pilot Environment ready
  O365 users migrated to On-Prem
  Pilot migrations completed
  All migrations completed
  <R018>If all O365 users do not have 02013 deployed till October it will push out all project plan until they do. Mitigation: Decision approved on SteerCo that O365 users that can not be upgraded to 02013 would be left in O365 with no free/busy information available for them, until they are uplifted and migrated.
  <R011> Only users with 0ffice2013 deployed can be migrated to Exchange on premises solution. If Office2013 project delays this would directly impact this project delivery timelines. Mitigation: Close collaboration with Office2013 project.
  <R004> Specific historical Danske Bank requirements might require custom development as not available as Exchange out of the box functionality. Mitigation: Self Service functionality delivery on Portal agreement.
  Production environment HW ordering initiated
  Pass 3 Migration for 0365 users started on 10th of Sep
  Package for PDF conversion tool distributed to >90% of ALL users
  Calendar SQL database integration with Pilot environment initial showing 16 time better results than with O365
  Jet Stress test run completion on Pilot environment with satisfactory results
  Pass3 migration completion –15th of September
  Data clean up in Lotus Notes after Pass3 – 18th of September
  Configuration and Non Functional Test cases run on the Pilot environment – 30th of September
  Start of O365 users data synchronization – 5th of October
  DMZ environment workshop set for – 14th of October
  RMS deployment workshop set for – 15th of October
  RMS environment delivery and set up
Recent progress
Next period
Critical milestones
Top Risks and issues
Key objective of New Messaging Service project is delivery of a new messaging platform that will enable well performing and reliable e-mail and calendar capabilities to all Danske Bank group. This objective will be achieved by delivering Microsoft Exchange 2013 platform on premises which will enable use of Outlook 2013 for e-mail and calendar instead of Lotus Notes/O365 platforms as well as the migration of the data to the new platform.
Completed
Completed
Completed Completed 2015 09 30
2015 10 30
2015 12 30
2016 06 30
Rationale for project status
Pilot environment non-functional testing activities in progress as per agreed milestones.
Path to Green
n/a

## Slide 3
 | 2015 |  |  |  |  |  |  |  |  | 2016 |  |  |  |  | 
 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
Initiation |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Solution Definition |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pilot Set up |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pilot Migration |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Production Set up |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Production Migration (by iterations) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Decommissioning |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Office 2013 Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Appendix 1 – High Level Timeline
WO sign with MS
Reqs definition
Reqs assessment
Planning
Solution Alignment WS
Principle HW requirements agreed
AD changes
Refresh of Co-Existence environment
Detailed Design
HW Delivery
Pilot Set up
Migration environment upgrade
Pilot environment testing
O365 users migration
Selected LN users migration and ex O365 users Pass3 migration
HW Delivery
Set up
Full Migration from LN – Migration Factory
(target: ~2500 users per iteration)
1
On-Track
At Risk
Legend
Complete
2
3
Pilot users migrated to Office 2013
Users in iteration migrated to Office 2013
Critical Dependencies:
O365 users migrated to Office 2013
1
2
3
Late
1st SteerCo
Detail Plan updates following specific functionality estimation
3
3
3
3
3
3
3
Planning
Migrations Complete
Testing
Resolution and deployment to all by iterations
Migration environment test (Migration test toO365)
Specific functionality delivery estimation
RMS set up
Operational Readiness
End-User Readiness
DMZ environment insource and upgrade planning
Today
Estimation