## Slide 1
  Clear definition of what “World Class” is must be defined – should the benchmark be industry or generic process benchmarking?
  Master Planning has to shift from capacity planning in line /country organisation to Global team organisation over the next 1½ year. This organisation will be defined gradually, and master planning needs to encompass both organisational structures.
  Master data update will be behind schedule as a few sections will not begin using updated time registration until aug-sept (reason for “Yellow” on plan)
Right capacity at the right place to handle customer demand (planning)
Increased performance on Quality, Delivery and Cost
Faster reaction to abnormal conditions
Improve Group Operations capabilities within both Operations planning and performance management
Agree on and build an improved planning and performance infrastructure that will facilitate Group Operations on its way to World Class capabilities
Ensure training, knowledge and experience sharing, and other types of competency development activities
  All employees in OP&PP has been trained in Tableau reporting and 2 – 3 employees have been assigned for a performance dimension to develop
  No results output wise, and that is neither the plan – but development work progressing as indicated in next steps
  Productivity Tableau report is functioning, yet not finished yet
  Employee motivation report is functioning, yet not finished yet
Initiative: World-Class Planning and performance capabilities
Jan 1 2015
Customer service
Dec 15 2015
Basic facts
Project Scope
Expected benefits (CASE)
Key benefit
End date
Start date
Kim Winther
Responsible
Challenges
Key results:
Next steps
KPI summary
Plan
Resource
Costumer attention
Simplicity
Efficiency
On track
Small deviation
Large deviation
N/A
July15
June15
Aug15
Sept 15
Performance dimensions “Quality” and “Continuous improvement” awaits Infrastructure projects suggestions to metrics
Delivery and Utilization in Tableau
Clarify Global teams org
Start up case inflow stats + S&OP start up for new areas (OPS SE)
Start up data extract for backlog and delivery performance (OPS SE)
Master data update OPS UK
Master data update OPS NO
“Handbook” for Planning & Performance assistance for Global team build up
(Part of implementation activities)
Teams
Quality & Customer Service

## Slide 2
  Measurements has to shift from line /country organisation to Global team organisation over the next 1½ year. This organisation will be defined gradually, and measurements needs to encompass both organisational structures.
Improved customer experience by more exact delivery agreements
Improved planning capabilities in Group Operations by backlog overview
Important stepping stone for Global Teams
  Expand system based delivery performance and backlog measurements to all GO units
Supplement and change present delivery performance measurement from backlog based to case specific and improve customer impact indicators
  Increase customer specific delivery performance measurements (2015 scope)
  Project sponsored by Group Operations Management has provided better data support for reliable delivery performance measurements
  E2E process measurement reports being developed allows new sources of reliable delivery performance measurements
Initiative: Delivering against SLAs – Improve Measures
Jan 1 2015
Customer service
Dec 15 2015
Basic facts
Project Scope
Expected benefits (CASE)
Key benefit
End date
Start date
Kim Winther
Responsible
Challenges
Special focus on reusing E2E data for Operations delivery performance
Further refinement of measurement infrastructure to incorporate deadline controlled performance
Key results:
Next steps
KPI summary
Plan
Resource
Costumer attention
Simplicity
Efficiency
On track
Small deviation
Large deviation
N/A
Quality & Customer Service
June15
May15
Jul15
Aug 15
Clarify Global teams org
Start up case inflow stats + S&OP start up for new areas (OPS SE)
Start up data extract for backlog and delivery performance (OPS SE)